## Roadmap to Numista.AI Productio
Phase | Timeline | Primary Objective
Phase 1: Foundation | Apr - June 2026 | Migrate the Firestore schema and build the Flutter "Shell" (Web & Mobile).
Phase 2: The Core | July - Sept 2026 | Rebuild the AI "Deepdive" and Invoice Scanning into the new UI.
Phase 3: The Lens | Oct - Nov 2026 | Integrate the "Auto-Capture" Microscope and High-Res imaging logic.
Phase 4: Launch | 2026-12-01 | Final Security Audit, Estate Planning features, and Public Release.